## Φύλλο1
Statement of facts at port of Police (Discharging Port)
Bill of lading quantity: 20.250 mts rock phospahte
Wed | 2014-03-05 | 7:00 | Vessel Arrived at roads
|  | 07:30-08:30 | Shifted to designed berth
|  | 8:30 | Vessel berthed
|  | 8:30 | Nor Tendered
|  | 10:00 | Customs Onboard
|  | 11:00 | Free Pratique Granded / Customs Cleared
|  | 12:20 | NOR Accepted as per Charter party
|  | 12:30-13:30 | Draft survey
|  | 13:40 | Discharging Commenced
Thu | 2014-03-13 | 14:00 | Discharging Completed
No Holidays during vessel's stay.
Office Hours: 08:00-16:00 Monday to Friday
Day | Date | Hours worked |  | Hours Stopped |  | Remarks
|  | From | To | From | To
Wed | 2014-03-05 |  |  | 12:30 | 13:30 | draft survey
|  |  |  | 13:30 | 13:40 | no work - waiting for discharging
|  | 13:40 | 20:00 |  |  | discharging
|  |  |  | 20:00 | 22:00 | shore stoppage
|  | 22:00 | 24.00 |  |  | discharging
Thu | 2014-03-06 | 0:00 | 21:00 |  |  | discharging
|  |  |  | 21:00 | 24.00 | no work - rain
Fri | 2014-03-07 |  |  | 0:00 | 1:00 | as above
|  | 1:00 | 24.00 |  |  | discharging
Sat | 2014-03-08 | 0:00 | 18:00 |  |  | as above
|  |  |  | 18:00 | 24.00 | no work - weekend
Sunday | 2014-03-09 |  |  | 0:00 | 15:00 | as above
|  | 15:00 | 22:00 |  |  | discharging
|  |  |  | 22:00 | 24.00 | no work - weekend
Monday | 2014-03-10 |  |  | 0:00 | 6:00 | as above
|  |  |  | 6:00 | 8:00 | no work - rain
|  | 8:00 | 24.00 |  |  | Discharging
Tue | 2014-03-11 |  |  | 0:00 | 24.00 | no work - rain
Wed | 2014-03-12 | 0:00 | 5:00 |  |  | Discharging
|  |  |  | 5:00 | 10:00 | no work - rain
|  | 10:00 | 24.00 |  |  | discharging
Thu | 2014-03-13 | 0:00 | 14:00 |  |  | discharging - discharging completed
|  | 14:00 | 15:00 |  |  | draft survey
|  | 15:00 | 17:00 |  |  | preperation for sailing
|  | 17:00 | 18:00 |  |  | Outwards clearance - Vessel sailed